## Week 1 Plan
Orion MVP - Week 1 Goal Tracker
Focus: text Q&A, web search, PDF/DOCX reader, lightweight routing, response synthesis
Day | Goal | Task | Module/File | Priority | Status | Deliverable | Success Check | Risk | Owner
Day 1 | Project setup | Create repo structure and config | app/main.py, services/assistant_service.py | High | Complete | Runnable CLI entry | App starts and accepts query | Env/config issues | You
Day 1 | LLM base | Add one working LLM client | interfaces/llm/openai_client.py | High | Not Started | Basic text answer path | Question -> answer works | API/auth issues | You
Day 2 | Orchestration | Implement simple orchestration flow | core/agent/orchestrator.py | High | Not Started | Route + gather + respond flow | No-tool query works cleanly | Overengineering router | You
Day 2 | Web skill | Build web search wrapper | skills/web_search.py | High | Not Started | Search results returned as text context | Current query triggers web | Search failures/empty results | You
Day 3 | File skill | Read PDF text safely | skills/file_reader.py | High | Not Started | PDF extraction path | PDF summary works | Unreadable PDFs | You
Day 3 | File skill | Read DOCX text safely | skills/file_reader.py | High | Not Started | DOCX extraction path | DOCX summary works | Messy formatting in docs | You
Day 4 | Routing logic | Add if/else routing for query + file | core/agent/orchestrator.py | High | Not Started | LLM vs web vs file routing | Correct tool chosen in common cases | False routing decisions | You
Day 4 | Synthesis | Combine query + tools into final answer | skills/response_synthesizer.py | High | Not Started | Coherent final response | Answer includes useful merged context | Prompt too messy | You
Day 5 | Fallbacks | Handle bad input and unsupported files | skills/file_reader.py, services/assistant_service.py | Medium | Not Started | Graceful error messages | System does not crash | Unhandled edge cases | You
Day 5 | Testing | Create smoke tests for main paths | tests/test_orchestrator.py | Medium | Not Started | Basic tests | Main flows pass locally | Missing edge-case tests | You
Day 6 | Polish | Improve prompt templates and formatting | skills/response_synthesizer.py | Medium | Not Started | Cleaner outputs | Answers are readable and structured | Over-tuning prompts | You
Day 6 | Integration | Manual end-to-end test with PDF + web | All core files | High | Not Started | Integrated MVP demo | All core use cases work | Integration bugs | You
Day 7 | Buffer + review | Fix bugs and freeze Week 1 scope | Whole project | High | Not Started | Stable MVP build | Week 1 success criteria met | Scope creep | You
Week 1 Success Criteria
- Ask a normal question -> get a useful answer
- Attach a PDF -> get a summary
- Ask a current-topic question -> web search is used
- System handles messy or unsupported input without crashing
- Codebase remains small and understandable
Notes
Keep Week 1 limited to text-based research assistant behavior. Do not add voice, wake word, memory, or full agent autonomy this week.
Generated: 2026-04-29 07:37